Azure Function Apps
In-Process to Isolated Worker Migration

Migration Approach & Impact Analysis

| Item | Project Context |
| --- | --- |
| Purpose | Manager review / migration planning |
| Current estate | .NET 6 and .NET 8 C# Function Apps, Functions v4, in-process |
| Hosting | Windows Function Apps on Premium / Elastic Premium tiers |
| Infrastructure | Terraform deployed through GitHub Actions |
| Application deployment | Azure DevOps / Deployment Center |
| Target | .NET 10 + Functions v4 + isolated worker, subject to compatibility |
| Deadline | 10 November 2026 |

# 1. Executive Summary

The current estate contains C# Azure Function Apps using the in-process execution model on Azure Functions 4.x, with applications targeting .NET 6 and .NET 8. Microsoft support for the .NET in-process model ends on 10 November 2026. .NET 6 is already out of official support. The applications therefore need to be migrated to the isolated worker model before the deadline.

The recommended approach is application-led: assess each Function App, select a supported target, migrate the local C# project and dependencies, build and test locally, then align the Azure/Terraform configuration and deploy through the existing DEV → GTEST → UAT → PROD process. The existing Windows Premium/Elastic Premium hosting should be retained where it supports the target; a hosting-plan redesign should not be assumed.

For the 2026 migration, .NET 10 is the proposed standard target where the application's dependencies support it. Microsoft currently lists .NET 10 as a supported isolated-worker target for Functions 4.x, with support through 14 November 2028.

Key principle: do not switch a production app to FUNCTIONS_WORKER_RUNTIME=dotnet-isolated while the deployed artifact is still an in-process application. Code and Azure configuration must be coordinated.

# 2. Current State

| Area | Current State | Implication |
| --- | --- | --- |
| Functions runtime | v4.x | Keep v4.x |
| Execution model | C# in-process | Must migrate |
| .NET | Some .NET 6; some .NET 8 | .NET 6 is already unsupported; .NET 8 in-process support ends with in-process retirement |
| OS | Windows | Retain unless app-specific issue |
| Hosting | Premium / Elastic Premium; reported P2v2/Premium v2 and Elastic Premium | Assess and retain where compatible |
| IaC | Terraform / GitHub Actions | Update only required runtime/app settings |
| App deployment | Azure DevOps / Deployment Center | Keep existing delivery model with pipeline updates if required |

# 3. Target State

| Component | Target |
| --- | --- |
| Functions runtime | v4.x |
| Execution model | Isolated worker |
| .NET | 10.0 where compatible; document exceptions |
| Worker setting | FUNCTIONS_WORKER_RUNTIME=dotnet-isolated |
| OS | Windows |
| Hosting | Existing Premium/Elastic Premium where compatible |
| Infrastructure | Terraform remains source of truth |
| Application delivery | Existing Azure DevOps deployment process |

# 4. Migration Strategy

## Phase 1 – Inventory and Assessment

Identify every in-process Function App across DEV, GTEST, UAT and PROD.

Capture .NET version, Functions runtime, OS, hosting plan, worker runtime, triggers, bindings, NuGet packages, external dependencies, identity, Key Vault, Service Bus, Storage, Application Insights and networking.

Identify applications already using isolated worker so they are excluded from the migration scope.

Create one migration tracker with owner, complexity, dependencies, test status and target release.

## Phase 2 – Target and Compatibility Assessment

Use .NET 10 isolated worker as the standard target when application dependencies support it.

Review third-party libraries, APIs, binding packages, Durable Functions usage, custom startup code and HTTP-specific APIs.

Document any application that cannot target .NET 10 and agree an alternate supported target.

## Phase 3 – Application Code Migration

Update the project SDK and TargetFramework.

Replace in-process Functions SDK/package references with isolated worker packages.

Add or update Program.cs and worker/host configuration.

Change function attributes and signatures, for example [FunctionName] to [Function].

Review and migrate HTTP, Service Bus, Blob, Timer, Queue, Event Grid and other bindings.

Migrate dependency injection and startup configuration.

Review ILogger/logging configuration and Application Insights integration.

Review configuration, environment variables, Key Vault references and managed identity use.

Update automated tests and mocks for isolated worker behavior.

## Phase 4 – Build and Local Validation

Restore packages and build with the target .NET SDK.

Run Azure Functions Core Tools v4 locally.

Execute every trigger path with representative payloads.

Validate external integrations, identity, retries, error handling and logging.

Fix compatibility issues before Azure deployment.

## Phase 5 – Infrastructure Alignment

Review the Terraform resource for the migrated Function App.

Update the runtime stack to the selected target where required.

Set FUNCTIONS_WORKER_RUNTIME to dotnet-isolated as part of the coordinated deployment.

Validate 64-bit configuration and all existing storage, identity, networking and monitoring settings.

Run terraform plan and review the change before apply.

Do not recreate the Function App unless a specific hosting/runtime constraint requires it.

## Phase 6 – Environment Rollout

Deploy the migrated application to DEV.

Apply the corresponding DEV infrastructure/runtime configuration.

Perform functional and integration testing.

Promote to GTEST and UAT after approval.

Validate monitoring, dependencies, performance, retry behavior and business transactions.

Promote the same tested artifact/configuration to PROD through the normal change process.

Perform post-production smoke testing and monitoring.

# 5. Application Impact Analysis

| Area | In-Process → Isolated Impact |
| --- | --- |
| Project file | Change target/SDK and Functions worker packages |
| NuGet packages | Replace in-process SDK and review binding extension packages |
| Program.cs | Introduce/update isolated worker host and service configuration |
| Function syntax | Review [FunctionName] and signatures; isolated uses [Function] |
| Bindings | Review every trigger/input/output binding and supported types |
| Dependency Injection | Move startup/service registration to standard worker host configuration |
| Logging | Review ILogger and worker logging configuration |
| Application Insights | Review worker-service and Functions integration |
| HTTP functions | Review request/response types and ASP.NET Core integration if used |
| Configuration | Review local.settings.json, app settings and Key Vault references |
| Tests | Update test setup/mocks and execute integration tests |
| Third-party dependencies | Confirm .NET 10 compatibility |

# 6. Infrastructure / Terraform Impact

The infrastructure change is a coordinated configuration change, not automatically a rebuild of the Function App. The exact Terraform resource must be reviewed per application.

Functions runtime remains v4.x.

Current Windows hosting can be retained where compatible.

Runtime stack should be aligned with the selected .NET target.

FUNCTIONS_WORKER_RUNTIME changes from dotnet to dotnet-isolated for the migrated app.

Existing storage, managed identity, Key Vault, Service Bus, networking and Application Insights should be retained unless assessment identifies a compatibility issue.

Use Terraform plan/review before applying production changes.

Keep infrastructure deployment in the existing GitHub Actions process.

# 7. CI/CD Approach

| Pipeline | Responsibility | Migration Approach |
| --- | --- | --- |
| GitHub Actions / Terraform | Infrastructure | Update only required runtime/app settings; review plan and apply by environment |
| Azure DevOps / Deployment Center | Application | Build and deploy the migrated isolated-worker artifact |
| Release/change process | Promotion | DEV → GTEST → UAT → PROD with approvals and evidence |

# 8. Testing Strategy

| Test Area | Required Validation |
| --- | --- |
| Build | Clean restore/build using target .NET SDK |
| Triggers | Every trigger executes successfully |
| Bindings | Input/output behavior matches current business behavior |
| Integrations | Service Bus, Storage, Key Vault, APIs and databases |
| Identity | Managed identity and authentication continue to work |
| Logging | Expected logs and Application Insights telemetry are available |
| Errors/retries | Failure and retry behavior remains correct |
| Performance | Baseline and post-migration behavior compared |
| Business validation | UAT confirms functional equivalence |
| Production | Smoke test plus enhanced monitoring after release |

# 9. Key Risks and Mitigations

| Risk | Mitigation |
| --- | --- |
| Binding/API differences | Inventory every trigger/binding and test each one |
| NuGet incompatibility | Review dependency tree and target .NET compatibility |
| Runtime/config mismatch | Deploy isolated artifact and dotnet-isolated configuration together |
| Configuration/identity issue | Compare settings, Key Vault references and managed identity behavior |
| Production regression | Progressive environment rollout, approvals and rollback plan |
| Terraform drift | Mandatory terraform plan review |
| Deadline risk | Prioritize .NET 6 and high-risk production apps early |

# 10. Rollback Strategy

Keep the last known-good artifact and infrastructure configuration available until production validation is complete.

Use deployment slots where available and appropriate.

Version-control Terraform changes and restore through the normal change process if rollback is required.

Define rollback criteria before production: startup failure, missing triggers, failed critical integrations, abnormal error rate or business transaction failure.

Capture logs/root cause before a second migration attempt.

# 11. Recommended First Migration

Do not start by migrating every production application simultaneously. Select one representative .NET 8, Windows, Premium/Elastic Premium Function App with common trigger/binding patterns and migrate it end-to-end. This creates the standard pattern for the rest of the estate.

Select representative application.

Complete inventory and dependency assessment.

Create migration branch.

Migrate code/project to isolated worker and target .NET 10.

Build and test locally.

Deploy to DEV and align DEV infrastructure.

Promote through GTEST and UAT.

Document lessons learned and standardize the migration checklist.

Use the proven pattern for the remaining applications.

Prioritize .NET 6 applications because .NET 6 is already out of official support.

Complete all production migrations with buffer before 10 November 2026.

# 12. Migration Tracker Template

| Function App | Env | Current .NET | Model | Hosting | Target | Code | DEV | GTEST | UAT | PROD |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TBD | TBD | 6/8 | In-process | Premium/Elastic Premium | 10 Isolated | Not started | - | - | - | - |
| TBD | TBD | 6/8 | In-process | Premium/Elastic Premium | 10 Isolated | Not started | - | - | - | - |
| TBD | TBD | 6/8 | In-process | Premium/Elastic Premium | 10 Isolated | Not started | - | - | - | - |

# 13. Conclusion and Recommendation

The recommended migration is an application-led conversion from C# in-process to the isolated worker model, followed by coordinated Azure/Terraform configuration changes. The main technical work is not simply changing the runtime stack: the project file, worker packages, Program.cs, function attributes/signatures, bindings, dependency injection, logging, configuration and monitoring must be reviewed and tested.

The current Windows Premium/Elastic Premium hosting model should be retained where it supports the target. The existing Terraform/GitHub Actions and Azure DevOps deployment separation should also be retained. A representative application should be migrated first to establish the standard migration pattern, followed by controlled rollout across the remaining Function Apps.

Immediate next action: complete the Function App inventory and obtain the Terraform resource plus .csproj/code for the first representative application. Use that application to validate the exact infrastructure changes and code impact before applying the pattern to the wider estate.

# 14. Microsoft References

Migrate C# Apps from In-process to Isolated Worker Model: https://learn.microsoft.com/azure/azure-functions/migrate-dotnet-to-isolated-model

Differences between isolated worker and in-process .NET Azure Functions: https://learn.microsoft.com/azure/azure-functions/dotnet-isolated-in-process-differences

Compare Azure Functions Runtime Versions: https://learn.microsoft.com/azure/azure-functions/functions-versions

Guide for running C# Azure Functions in an isolated worker process: https://learn.microsoft.com/azure/azure-functions/dotnet-isolated-process-guide